## Sprint 1
Functional Testing Case Study
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://www.ebay.com/ Module: REGISTRATION, LOGIN & BUY ITEMS
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the Depndacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Ebay is the online application for buying items It supports various functionalities such as user registration, login, searching for a product, add items to cart and payments. It is developed by the authors. It supports multiple browsers such as IE, Firefox, Chrome. In scope Functionality: Ebay provides following functionalities to the end user : 1. Signup Page & Login page: a. Validate the sign up using Firstname, lastname, email, password. or using Gmail b. Validate the login page using either by Email and password or using gmail 3. Search an item a. Search Product on various categories - Electronics, Fashion, Healthy and beauty, etc b. View the products availability c. Add to cart 4. Buy items a. Enter shipping address b. Enter billing address c. Enter the payment details d. Enter the delivery details e. Discount coupons 5. Confirm Order a. Download and acknowledge the receipt 6. Sell an item a. View the suggested keywords b. Post an advertisement c. Add items to free list Out of Scope Functionality: 1. Cancel the order 2. Any other functionalities Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing QA Suggestions:- 1) Localization Testing most important 2) Exchange Rate (That Means Gobal Currency values should show correctly as per selected currency) 3) UI Testing 4) Scenario based Testing such as basic, alternate etc.
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report
Sprint Day 5 | Sprint Evaluation

## User_Stories
Registration module
Issue Type | Summary
Epic 1 | Verify Registration functionality
Story 1 | As a new user, I should be able to register my details into the application, so that I can perform required activity
Task 1 | As a user I want to register my details to application in order to keep track of my activities
Subtask 1 | Create new account
Login module
Epic 2 | Verify Login functionality
Story 1 | As a user, I should be able to login in by providing the registered email and password
Task | Verification of the user after entering valid email and password
Story 2 | As a user, i should receive a error message when am entering the wrong email or password.
Task | Verification of the user after entering Invalid email and password.
Story 3 | As a user, It should remember the account by clicking checkbox and delete remembered account after clicking logout.
Search module
Epic 4 | Verify the search product functionality.
Story 1 | As a user, I should able to access search textbox for searching various products
Story 2 | As a user, I should able to select the interested product and add to cart.
Story 3 | As a user, I should receive a error message "No records matched your search criteria" when the user searching for unrelated data.
Product module
Epic 5 | Buy the product
Story 1 | As a user, I want to buy an item by providing quantity and checkout
Story 2 | As a user, I want to enter the shipping address
Story 3 | As a user, I want to enter the billing address
Story 4 | As a user, I want to enter the credit card details
Story 5 | As a user, I want to enter the discount coupon
Receipt module
Epic 6 | Download the receipt
Story 1 | As a user I want to download the receipt
Task 1 | Click on the Download button to download the receipt
Story 2 | As a user I want to print the receipt
Task 1 | Click on the Print button to print the order receipt
Story 3 | As a user, I want to acknowlege the purchase
Task 1 | The user should receive an order confirmation email with order details on registered email ID after placing an order

## Scenarious
TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
TS_ebay_01 | REQ_01 | To verify the URL for Ebay on Google browser. | Functional testing | 1 | validating the URL navigates to Ebay site.
TS_ebay_02 | REQ_02 | To verify that the user redirects to the sign up page | Functional testing | 1 | Validate the successful navigation of sign up page
TS_ebay_03 | REQ_03 | To verify that the user enters the valid gmail or facebook or mobile number | Functional testing | 6 | Verifying the user details entered by the user.
TS_ebay_04 | REQ_04 | To verify the user is able to search for an item in the application | Functional testing | 2 | Verifying the user is able to search for an item
TS_ebay_05 | REQ_05 | To verify the user is able to view the deals of the week | Functional testing | 1 | Validating the URL navigates to deals of the week page
TS_ebay_06 | REQ_06 | To verify the user is able to buy an item | Functional testing | 10 | Verifying the user details entered by the user.
TS_ebay_07 | REQ_07 | To verify the user is able to view the offers | Functional testing | 1 | Validating the URL navigates to offfers page
TS_ebay_08 | REQ_08 | To verify the user is able to apply discount coupon when purchasing an item | Functional testing | 2 | Validating the discount coupon
TS_ebay_09 | REQ_09 | To verify the user is able to search for multiple items in the list | Functional testing | 2 | Validating the cart

## Testcase
Test Case ID | Test Scenario | Precondition | Test Condition | Step Number | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1)
TC_01 | TS_ebay_01 | User has internet connection | To verify the URL for ebay on Google browser. | Step 1 | Type the URL in the browser and press <<enter>> key | https://www.ebay.com/ | Application naviages to HOME page | Application navigated to HOME page | Pass
TC_02 | TS_ebay_02 | User is in the HOME page | To verify that the user redirects to the sign up page | Step 1 | Click on the sign up link |  | Application navigates to sign up page | Application navigated to sign up page | Pass
TC_03 | TS_ebay_03 | Usre is in the Sign up page | To verify that the user enters the valid gmail or facebook or mobile number | Step 1 | Click on the link Gmail |  | Gmail login window appears | Gmail login window appeared | Pass
|  |  |  | Step 2 | Enter the email |  | Email appears | Email appeared
|  |  |  | Step 3 | Enter the password |  | Encrypted password appears | Encrypted password appeared
|  |  |  | Step 4 | Click on Submit |  | User reaches the HOME page with the welcome message | User reached the HOME page with the welcome message
TC_04 | TS_ebay_03 | Usre is in the Sign up page | To verify that the user enters the valid gmail or facebook or mobile number | Step 1 | Click on the link facebook |  | FB login window appears | FB login window appeared | Pass
|  |  |  | Step 2 | Enter the username |  | Email appears | Email appeared
|  |  |  | Step 3 | Enter the password |  | Encrypted password appears | Encrypted password appeared
|  |  |  | Step 4 | Click on Submit |  | User reaches the HOME page with the welcome message | User reached the HOME page with the welcome message
TC_05 | TS_ebay_03 | Usre is in the Sign up page | To verify that the user enters the valid gmail or facebook or mobile number | Step 1 | Click on the link Mobile |  | Mobile page window appears | Mobile page window appeared | Pass
|  |  |  | Step 2 | Enter the mobile number |  | Mobile number appears | Mobile number appeared
|  |  |  | Step 3 | Click on Submit |  | OTP generated and appears in mobile | OTP generated and appears in mobile
|  |  |  | Step 4 | Enter the OTP and submit |  | User reaches the HOME page with the welcome message | User reaches the HOME page with the welcome message
TC_06 | TS_ebay_03 | Usre is in the Sign up page | To verify that the user enters the invalid gmail or facebook or mobile number | Step 1 | Click on the link Gmail |  | Gmail login window appears | Gmail login window appeared | Pass
|  |  |  | Step 2 | Enter the invalid email | tester@gmail.com | Email appears | Email appeared
|  |  |  | Step 3 | Enter the password |  | Encrypted password appears | Encrypted password appeared
|  |  |  | Step 4 | Click on Submit |  | System displays "Invalid username or password" | System displayed "Invalid username or password"
TC_07 | TS_ebay_03 | Usre is in the Sign up page | To verify that the user enters the invalid gmail or facebook or mobile number | Step 1 | Click on the link facebook |  | FB login window appears | FB login window appeared | Pass
|  |  |  | Step 2 | Enter the invalid username | wrongemail@gmail.com | Email appears | Email appeared
|  |  |  | Step 3 | Enter the password |  | Encrypted password appears | Encrypted password appeared
|  |  |  | Step 4 | Click on Submit |  | System displays "Invalid username or password" | System displayed "Invalid username or password"
TC_08 | TS_ebay_03 | Usre is in the Sign up page | To verify that the user enters the invalid gmail or facebook or mobile number | Step 1 | Click on the link Mobile |  | Mobile page window appears | Mobile page window appeared | Pass
|  |  |  | Step 2 | Enter the invalid mobile number | -343434343343 | Mobile number appears | Mobile number appeared
|  |  |  | Step 3 | Click on Submit |  | System displays "invalid mobile number" | System displayed "invalid mobile number"

## Defects
Defect Id. | Module name | Defect Summary | Description | Actual output | Defect Priority | Assigned To | Status | Screenshot
DF_01 | Login | User is unable to login with Invalid credentials. | Steps : 1. Open URL. 1. Login to ebay. 2. Enter user name in "User name filed" 3. Enter password. 4. Click on "Login" button 5. Verify whether User is able to login with valid credentials. | User is not able to login with Invalid credentials | High | shennen.jospeh@capgemini.com | Active
DF_02 | Admin | ESS Supervisor is not able view his subordinates Employee personal details. | Steps : 1. Login to ebay. 2. Open ADmin module. 3. Click on Userrole in Admin module. 4. Select role ESS and search. 5. Click on subordinate details. | ESS-Supervisor is not able to view his subordinate personal details | Medium | ABC@capgemini.com | Active

## RTM
Req No. | Req Desc | TestScenario ID | Status
REQ_3 | To Verify the Login Functionalities . | TC_03, TC_04, TC_05, TC_06, TC_07, TC_08 | TC_03 - Pass
TC_04 -Pass
TC_05 -Pass
TC_06 -Pass
TC_07 --Pass
TC_08 -Pass

## Test summary Report
Test Summary Report
Test Cycle System Test
EXECUTED | 28 | PASSED | 26
|  | FAILED | 2
(Total)TESTS EXCUTED (PASSED+FAILED)
PENDIING |  | 2
IN PROGRESS |  | 0
BLOCKED |  | 0
(Sub-Total) TEST PLANNED
(PENDING+INPROGRESS+BLOCKED+TEST+EXECUTED)
Function | Description | No of TCs Executed | No of TCs Passed | TCs pending | Priority | Remarks
Login Functionalities | Verify that user should be able to login to https://ebay.com/ succesfully | 8 | 8 | 0 | High

## Sprint 2
Automation Testing Case Study - 1
Following website is given for Automating Testing using Selenium Automation Page Factory/POM, TestNG & BDD Framework (using Cucumber)
Url: https://www.ebay.com/
Sprint Day # | Task / Scenario Given | Deliverables at the EoS Day#
Sprint Day 1 | 1. Java Case study completion individually | 1. Case Study implementation code
| 2. Identify the Manual Test Cases that you want to automate. | 2. Test Cases: Positive & Negative
| 3. Plan the flow of application that you want to test using automation test scripts. | 3. Application Flows: Positive & Negative.
| 4. Create a Maven Project - Associate required libraries with the Maven Project | 4. Creation of project structure
5. Configure required dependencies like Selenium WebDriver, TestNG / Junit, Cucumber etc. in POM.xml
Sprint Day 2 | 1. Create the required Feature files with relevant scenarios (User Stories) using Gherkin. | 1. List of Feature Files :
| · Use Scenario Outline & Examples to implement Parametrization in Feature File | 2. List of Test Cases :
| 2. Implement Page Factory or Object Repository (XML/Property File) to identify and store all the web elements. | 3. Prioritization of tests :
| · Use all types of Locators | 4. Parametrization Sample Data :
| · Ensure appropriate usage of Selenium Web Driver API objects and import statements | 5. Any Test Suite?
| 3. Implement parametrization using apache POI | 6. Test Runner class Parameters
| 4. Implement TestNG for generating reports and XML file for parallel execution of test suite | 7. Report File Names
5. Design the test runner class
Sprint Day 3 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements. | 1. Detail Test Script in Step Definitions
| · Implement Assertions/Verifications using TestNG | 2. Feature File- Test Case – PF/OR collation in an Excel sheet
· Use appropriate wait statements
· Handle new windows, popup’s, navigations
2. Ensure implementation of good programing practices
· Variable, Function & procedure naming convention
· Usage of comments
· Code Indentation
Sprint Day 4 | 1. Generate Traceability Matrix based on Feature File User Stories, Test Scripts and Defects | 1. Traceability Matrix
| 2. Finally generate TestNG/XML Test report mentioning pass/fail status. | 2. Test Reports
| 3. Keep all code in Git repository | 3. Final execuatble code in Git
Sprint Day 5 | 1. Jenkins Implimentation 2. Project Closure | 1. Create build using Jenkins
Sprint Day 6 | Sprint Evaluation