## Sprint 1
Functional Testing Case Study
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report http://sampleapp.tricentis.com/101/ Module: Automobile, Truck, Motor cycle, Camper
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the De+B3pendacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Vehicle Insurance Calculator aims to search and view the details of Automobile, Truck, Motor cycle and Camper. The user can search, view Details and finally can apply for new insurance. In scope Functionality: Vehicle Insurance Calculator provides following functionalities to the end user : 1. Automobile Page : User can add the following parameters like Vehicle data, Insurant data, Product data, Price option and subsequently he can view the quotation 2. Truck User can add the following parameters like Vehicle data, Insurant data, Product data, Price option and subsequently he can view the quotation 3. Motor cycle User can add the following parameters like Vehicle data, Insurant data, Product data, Price option and subsequently he can view the quotation 4. Camper User can add the following parameters like Vehicle data, Insurant data, Product data, Price option and subsequently he can view the quotation Out of Scope Functionality: 1. Reserving tickets 2. Cancelling the tickets Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing QA Suggestions:- 1) Localization Testing most important 2) Exchange Rate (That Means Gobal Currency values should show correctly as per selected currency) 3) UI Testing 4) Scenario based Testing such as basic, alternate etc.
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report
Sprint Day 5 | Sprint Evaluation

## User_Stories
Sign In Module By Aman Jain
Issue Type | Summary
Epic 1 | verify insurance for automobile
Story 1 | As a user, I should be able to apply for the automobile, so that I can get the quotation
Tasks | 1. Select "Automobile" link on Home page 2. Enter the vehicle details 3. Enter the Insurant data 4. Enter the Product data 5. Enter the Price option
Story 2 | As a user, I should be able to apply for the truck, so that I can get the quotation
Tasks | 1. Select "Truck" link on Home page 2. Enter the vehicle details 3. Enter the Insurant data 4. Enter the Product data 5. Enter the Price option

## Sprint 2
Automation Testing Case Study
Following website is given for Automating Testing using Selenium Automation Page Factory/POM, TestNG & BDD Framework (using Cucumber)
http://sampleapp.tricentis.com/101/
Sprint Day # | Task / Scenario Given | Deliverables at the EoS Day#
Sprint Day 1 | 1. Identify the Manual Test Cases that you want to automate. | 1. Creation of Project Structure
| 2. Plan the flow of application that you want to test using automation test scripts. | 2. Creation of Feature File.
3. Create a Maven Project - Associate required libraries with the Maven Project
4. Configure required dependencies like Selenium WebDriver, TestNG / Junit, Cucumber etc. in POM.xml
5. Creation of Feature File
Sprint Day 2 | 1. Create the required Feature files with relevant scenarios (User Stories) using Gherkin continue. | 1. List of Feature Files :
| · Use Scenario Outline & Examples to implement Parametrization in Feature File | 2. List of Test Cases :
| 2. Implement Page Factory or Object Repository (XML/Property File) to identify and store all the web elements. | 3. Prioritization of tests :
| · Use all types of Locators | 4. Test Runner class Parameters
| · Ensure appropriate usage of Selenium Web Driver API objects and import statements | 5. Report File Names
3. Design the test runner class
Sprint Day 3 | 1. Implement parametrization using apache POI | 1. Parametrization Sample Data :
| 2. Implement TestNG for generating reports and XML file for parallel execution of test suite | 2. Report File Names
| 3. Generate Step Definitions and write the Tests addressing all the functional requirements. | 3. Generating Step Defination File
Sprint Day 4 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements | 1. Detail Test Script in Step Definitions
| · Implement Assertions/Verifications using TestNG | 2. Feature File- Test Case – PF/OR collation in an Excel sheet
· Use appropriate wait statements
· Handle new windows, popup’s, navigations
2. Ensure implementation of good programing practices
· Variable, Function & procedure naming convention
· Usage of comments
· Code Indentation
Sprint Day 5 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements Continue | 1. Detail Test Script in Step Definitions
2. Feature File- Test Case – PF/OR collation in an Excel sheet
Sprint Day 6 | 1. Generate TestNG/XML Test report mentioning pass/fail status.
1. Test Reports
Sprint Day 7 | 1. Jenkins Implimentation 2. Project Closure | 1. Create build using Jenkins
Sprint Day 8 | Sprint Evaluation