## SPRINT 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Repor http://examples.testsigma.com/ Module: REGISTRATION, LOGIN, SEARCH FOR FLIGHT, BOOK TICKETS, LOGOUT
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the Depndacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Test sigma demo is a online travel application. It supports various functionalities such as user registration, login, Search for flights, Book a travel , etc. It supports multiple browsers such as IE, Firefox, Chrome. In scope Functionality: Test sigma demo provides following functionalities to the end user : 1. Registration Page : Validate the Username, Password, Firstname, Lastname, Email, Phone, address1, address2, City, state, zip, country 2. Login a. Email : validate all fieldsa with valid and invlaid data. b. Password : validate with all options - valid and invlaid; the forgot password link, Sign-up link 3. Search for flights a. Search Flights on various categories - Economy, Business b. View the flights availability c. Book tickets 4. Confirm Booking a. View the ticket details Out of Scope Functionality: 1. Cancel the order 2. Any other functionalities Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing QA Suggestions:- 1) Localization Testing most important 2) Exchange Rate (That Means Gobal Currency values should show correctly as per selected currency) 3) UI Testing 4) Scenario based Testing such as basic, alternate etc.
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report
Sprint Day 5 | Sprint Evaluation

## User stories
Issue Type | Summary | Priority | Story point | Assign to
Epic 01 | Sign up | High
Story 1 | As a user, I should be able to register my details into the application, so that I can perform required activity |  | 5 | Yagavi M | 1 STORY POINT = 1 HOUR
Epic 02 | Log in | High
Story 1 | As a user, I should be able to login in by providing the registered Username and password |  | 2 | Yagavi M
Story 2 | As a user, I should receive a error message when am entering wrong username or password, so that I can know the security of application |  | 2 | Yagavi M
Epic 03 | Verify forgot password functionality | High
Story 1 | As a user, I should be able to reset my password by providing my email id and I should receive password reset link in email. |  | 2 | Ramana reddy
Story 2 | As a user, by accessing the password link, I should be able to reset my password. |  | 1 | Ramana reddy
Epic 04 | Search and select | High
Story 1 | As a user, I should able to access search textbox for searching various flights |  | 1 | Ramana reddy
Story 2 | As a user, I should receive a error message "No records matched your search criteria" when the user searching for unrelated data. |  | 1 | Ramana reddy
Story 3 | As a customer, I want to search a flight. So that, I can find best one. |  | 1 | Ramana reddy
Story 4 | As a customer, I want to select a product. So that, I can Order it. |  | 3 | Ramana reddy
Epic 05 | Booking a ticket | High
Story 1 | As a user, I want to book tickets, so that I can travel |  | 2 | Sandhya
Epic 06 | View tickets | High
Story 1 | As a User, I want to view the tickets in my account so that I can take the print |  | 2 | Sandhya