## SPRINT 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://www.saucedemo.com/ Module: LOGIN, BUY AN ITEM, LOGOUT
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the Depndacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Saucedemo is the sample commerce application It supports various functionalities such as user login, Search for product, Buy an item etc. It supports multiple browsers such as IE, Firefox, Chrome. In scope Functionality: Adantage online shopping provides following functionalities to the end user : 1. Login a. Email : validate all fieldsa with valid and invlaid data. b. Password : validate with all options - valid and invlaid; the forgot password link, Sign-up link 3. Search an item a. Search Product on various categories - Phones, Laptops, Monitors b. View the products availability c. Add to cart 4. Buy items a. Enter quantity b. Enter billing address c. Enter the payment details d. Enter the mode of delivery e. Enter card type f. Enter card number g. Enter expiry date 5. Confirm Booking a. View the order number Out of Scope Functionality: 1. Cancel the order 2. Any other functionalities Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing QA Suggestions:- 1) Localization Testing most important 2) Exchange Rate (That Means Gobal Currency values should show correctly as per selected currency) 3) UI Testing 4) Scenario based Testing such as basic, alternate etc.
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report
Sprint Day 5 | Sprint Evaluation

## User stories
Issue Type | Summary | Priority | Story point | Assign to
Epic 02 | Log in | High
Story 1 | As a user, I should be able to login in by providing the registered Username and password |  | 2 | Yagavi M | 1 STORY POINT = 1 HOUR
Story 2 | As a user, I should receive a error message when am entering wrong username or password, so that I can know the security of application |  | 2 | Yagavi M